## Estimation
|  |  | Totla Amount of Time = 6 people * 3 hours per day * 5 days * 5 weeks |  |  | Estimated Schedule
S No | Level1 |  | Level2 | Level3 | Level4 | Planning | Requiremnt | Desing | Imeplementation | Testing | Start | End | SE Kim | Sun | Tommy | Eom | Du | vijay | Total | Event Total Time
| Planning | Time spent planning, meetings and doc | Project Planning
Meetings
Scope discussion
Sprint Planning Meeting
Sprint Review Meeting
| Requirements | Req, analysis and doc | Requirements Study
Reuirements Analysis
ADS (FR, TC, BC, QA)
Meetings (with Mentor, Team, Customer)
| Design | Design, Meeting evaluations, doc | Architecture
|  |  | Design | DB Table Design | [6 empty] | 450
Tables for Customers (Name, Address, Phone, Order No, Order Date, Order Status)
Table for Orders (Order No, Order Date, Type of widgets, Quantity of Widgets, Order Status)
Table for Backordered Orders (Order No, Order Date)
Table for Widgets (Widget Type, Widget Quantity, Widgets at each station1, station2, station3)
Relationships of the tables
Primary Key and foreign keys in each table
|  |  |  | Customer App | Place Order | 1 | 1 | 1 |  |  | 2014-05-26 | 2014-05-26 |  |  | 1 |  |  | 1 | 2
|  |  |  | Customer App |  | 1 | 1 | 1
Place Order
Query Order Status
Display of Widgets
Supervisor App
Take Order
Monitor Order status
Monitor Overall status
Monitor robot status
Add Inventory
Debit inventory
Process Backordered order
Process order
Robot
Move
Load
Unload
Stop
| Implementation | development | Implementation
DB Table Impl
Tables for Customers (Name, Address, Phone, Order No, Order Date, Order Status)
Table for Orders (Order No, Order Date, Type of widgets, Quantity of Widgets, Order Status)
Table for Backordered Orders (Order No, Order Date)
Table for Widgets (Widget Type, Widget Quantity, Widgets at each station1, station2, station3)
Relationships of the tables
Primary Key and foreign keys in each table
Customer App
Place Order
Query Order Status
Display of Widgets
Supervisor App
Take Order
Monitor Order status
Monitor Overall status
Monitor robot status
Add Inventory
Debit inventory
Process Backordered order
Process order
Robot
Move
Load
Unload
Stop
Defect Fixing
| Testing | Test plan, Test cases dev, test cases execution | Test Plan
Test Cases Dev
Test Cases Exec
Integration Testing
Regression Testing
Defect logging into repository
Defect tracking

## Timelog
[7 empty] | 5/12~16 |  |  | 5/19~22 | 2014-05-26 | 2014-05-27 | 2014-05-28 | 2014-05-29 | 2014-05-30 | 2014-05-31 | 2014-06-01 | 2014-06-02 | 2014-06-03 | 2014-06-04 | 2014-06-05 | 2014-06-06 | 2014-06-07 | 2014-06-08 | 2014-06-09 | 2014-06-10 | 2014-06-11 | 2014-06-12 | 2014-06-13 | 2014-06-14 | 2014-06-15 | 2014-06-16 | 2014-06-17 | 2014-06-18 | 2014-06-19 | 2014-06-20 | 2014-06-21 | 2014-06-22 | 2014-06-23 | 2014-06-24 | 2014-06-25 | 2014-06-26 | 2014-06-27
S No | Level1 |  | Level2 | Level3 | Level4 | Resposibility | P | R | D
| Planning | Time spent planning, meetings and doc | Project Planning
Meetings
Scope discussion
Sprint Planning Meeting
Sprint Review Meeting
| Requirements | Req, analysis and doc | Requirements Study
Reuirements Analysis
ADS (FR, TC, BC, QA)
Meetings (with Mentor, Team, Customer)
| Design | Design, Meeting evaluations, doc | Architecture
|  |  | Design | DB Table Design
Tables for Customers (Name, Address, Phone, Order No, Order Date, Order Status)
Table for Orders (Order No, Order Date, Type of widgets, Quantity of Widgets, Order Status)
Table for Backordered Orders (Order No, Order Date)
Table for Widgets (Widget Type, Widget Quantity, Widgets at each station1, station2, station3)
Relationships of the tables
Primary Key and foreign keys in each table
|  |  |  | Customer App | Place Order
Customer App
Place Order
Query Order Status
Display of Widgets
Supervisor App
Take Order
Monitor Order status
Monitor Overall status
Monitor robot status
Add Inventory
Debit inventory
Process Backordered order
Process order
Robot
Move
Load
Unload
Stop
| Implementation | development | Implementation
DB Table Impl
Tables for Customers (Name, Address, Phone, Order No, Order Date, Order Status)
Table for Orders (Order No, Order Date, Type of widgets, Quantity of Widgets, Order Status)
Table for Backordered Orders (Order No, Order Date)
Table for Widgets (Widget Type, Widget Quantity, Widgets at each station1, station2, station3)
Relationships of the tables
Primary Key and foreign keys in each table
Customer App
Place Order
Query Order Status
Display of Widgets
Supervisor App
Take Order
Monitor Order status
Monitor Overall status
Monitor robot status
Add Inventory
Debit inventory
Process Backordered order
Process order
Robot
Move
Load
Unload
Stop
Defect Fixing
| Testing | Test plan, Test cases dev, test cases execution | Test Plan
Test Cases Dev
Test Cases Exec
Integration Testing
Regression Testing
Defect logging into repository
Defect tracking