## Estimation (hidden)
S No | Level1 |  | Level2 | Level3 | Level4 | Optimistic | Pessimistic | Most Likely | Estimate
| Planning | Time spent planning, meetings and doc | Project Planning | [5 empty] | 0
|  |  | Meetings | [5 empty] | 0
|  |  | Scope discussion | [5 empty] | 0
|  |  | Sprint Planning Meeting | [5 empty] | 0
|  |  | Sprint Review Meeting | [5 empty] | 0
| Requirements | Req, analysis and doc | Requirements Study |  |  | 5 | 6 | 7 | 6.5
|  |  | Reuirements Analysis | [5 empty] | 0
|  |  | ADS | [5 empty] | 0
|  |  | FR | [5 empty] | 0
|  |  | TC | [5 empty] | 0
|  |  | BC | [5 empty] | 0
|  |  | QA | [5 empty] | 0
|  |  | Meetings (with Mentor, Team, Customer) | [5 empty] | 0
| Design | Design, Meeting evaluations, doc | Architecture | [5 empty] | 0
|  |  | Design | DB Table Design |  |  |  |  | 0
[5 empty] | Tables for Customers (Name, Address, Phone, Order No, Order Date, Order Status) |  |  |  | 0
[5 empty] | Table for Orders (Order No, Order Date, Type of widgets, Quantity of Widgets, Order Status) |  |  |  | 0
[5 empty] | Table for Backordered Orders (Order No, Order Date) |  |  |  | 0
[5 empty] | Table for Widgets (Widget Type, Widget Quantity, Widgets at each station1, station2, station3) |  |  |  | 0
[5 empty] | Relationships of the tables |  |  |  | 0
[5 empty] | Primary Key and foreign keys in each table |  |  |  | 0
|  |  |  | Customer App | Place Order |  |  |  | 0
0
0
0
0
[5 empty] | Place Order |  |  |  | 0
[5 empty] | Query Order Status |  |  |  | 0
[5 empty] | Display of Widgets |  |  |  | 0
|  |  |  | Supervisor App |  |  |  |  | 0
[5 empty] | Take Order |  |  |  | 0
[5 empty] | Monitor Order status |  |  |  | 0
[5 empty] | Monitor Overall status |  |  |  | 0
[5 empty] | Monitor robot status |  |  |  | 0
[5 empty] | Add Inventory |  |  |  | 0
[5 empty] | Debit inventory |  |  |  | 0
[5 empty] | Process Backordered order |  |  |  | 0
[5 empty] | Process order |  |  |  | 0
|  |  |  | WareHouseServer |  |  |  |  | 0
|  |  |  | CommunicationProtocol |  |  |  |  | 0
|  |  |  | Robot |  |  |  |  | 0
[5 empty] | Move |  |  |  | 0
[5 empty] | Load |  |  |  | 0
[5 empty] | Unload |  |  |  | 0
[5 empty] | Stop |  |  |  | 0
|  |  | Review | Customer App |  |  |  |  | 0
|  |  |  | Supervisor App |  |  |  |  | 0
|  |  |  | WareHouseServer |  |  |  |  | 0
|  |  |  | Robot |  |  |  |  | 0
| Implementation | development | Implementation | [5 empty] | 0
|  |  |  | DB Table Impl |  |  |  |  | 0
[5 empty] | Tables for Customers (Name, Address, Phone, Order No, Order Date, Order Status) |  |  |  | 0
[5 empty] | Table for Orders (Order No, Order Date, Type of widgets, Quantity of Widgets, Order Status) |  |  |  | 0
[5 empty] | Table for Backordered Orders (Order No, Order Date) |  |  |  | 0
[5 empty] | Table for Widgets (Widget Type, Widget Quantity, Widgets at each station1, station2, station3) |  |  |  | 0
[5 empty] | Relationships of the tables |  |  |  | 0
[5 empty] | Primary Key and foreign keys in each table |  |  |  | 0
|  |  |  | Customer App |  |  |  |  | 0
[5 empty] | Place Order |  |  |  | 0
[5 empty] | Query Order Status |  |  |  | 0
[5 empty] | Display of Widgets |  |  |  | 0
|  |  |  | Supervisor App |  |  |  |  | 0
[5 empty] | Take Order |  |  |  | 0
[5 empty] | Monitor Order status |  |  |  | 0
[5 empty] | Monitor Overall status |  |  |  | 0
[5 empty] | Monitor robot status |  |  |  | 0
[5 empty] | Add Inventory |  |  |  | 0
[5 empty] | Debit inventory |  |  |  | 0
[5 empty] | Process Backordered order |  |  |  | 0
[5 empty] | Process order |  |  |  | 0
|  |  |  | WareHouseServer |  |  |  |  | 0
|  |  |  | CommunicationProtocol |  |  |  |  | 0
|  |  |  | Robot |  |  |  |  | 0
[5 empty] | Move |  |  |  | 0
[5 empty] | Load |  |  |  | 0
[5 empty] | Unload |  |  |  | 0
[5 empty] | Stop |  |  |  | 0
|  |  | Integration | Customer App |  |  |  |  | 0
|  |  |  | Supervisor App |  |  |  |  | 0
|  |  |  | WareHouseServer |  |  |  |  | 0
|  |  |  | Robot |  |  |  |  | 0
|  |  | Review | Customer App |  |  |  |  | 0
|  |  |  | Supervisor App |  |  |  |  | 0
|  |  |  | WareHouseServer |  |  |  |  | 0
|  |  |  | Robot |  |  |  |  | 0
|  |  | Defect Fixing | [5 empty] | 0
| Testing | Test plan, Test cases dev, test cases execution | Test Plan | [5 empty] | 0
|  |  | Test Cases Dev | [5 empty] | 0
|  |  | Test Cases Exec | [5 empty] | 0
|  |  | Integration Testing | [5 empty] | 0
|  |  | Regression Testing | [5 empty] | 0
|  |  | Defect logging into repository | [5 empty] | 0
|  |  | Defect tracking | [5 empty] | 0

## Timelog (hidden)
[7 empty] | 5/12~16 |  |  | 5/19~22 | 2014-05-26 | 2014-05-27 | 2014-05-28 | 2014-05-29 | 2014-05-30 | 2014-05-31 | 2014-06-01 | 2014-06-02 | 2014-06-03 | 2014-06-04 | 2014-06-05 | 2014-06-06 | 2014-06-07 | 2014-06-08 | 2014-06-09 | 2014-06-10 | 2014-06-11 | 2014-06-12 | 2014-06-13 | 2014-06-14 | 2014-06-15 | 2014-06-16 | 2014-06-17 | 2014-06-18 | 2014-06-19 | 2014-06-20 | 2014-06-21 | 2014-06-22 | 2014-06-23 | 2014-06-24 | 2014-06-25 | 2014-06-26 | 2014-06-27
S No | Level1 |  | Level2 | Level3 | Level4 | Resposibility | P | R | D
| Planning | Time spent planning, meetings and doc | Project Planning
Meetings
Scope discussion
Sprint Planning Meeting
Sprint Review Meeting
| Requirements | Req, analysis and doc | Requirements Study
Reuirements Analysis
ADS (FR, TC, BC, QA)
Meetings (with Mentor, Team, Customer)
| Design | Design, Meeting evaluations, doc | Architecture
|  |  | Design | DB Table Design
Tables for Customers (Name, Address, Phone, Order No, Order Date, Order Status)
Table for Orders (Order No, Order Date, Type of widgets, Quantity of Widgets, Order Status)
Table for Backordered Orders (Order No, Order Date)
Table for Widgets (Widget Type, Widget Quantity, Widgets at each station1, station2, station3)
Relationships of the tables
Primary Key and foreign keys in each table
|  |  |  | Customer App | Place Order
Customer App
Place Order
Query Order Status
Display of Widgets
Supervisor App
Take Order
Monitor Order status
Monitor Overall status
Monitor robot status
Add Inventory
Debit inventory
Process Backordered order
Process order
Robot
Move
Load
Unload
Stop
| Implementation | development | Implementation
DB Table Impl
Tables for Customers (Name, Address, Phone, Order No, Order Date, Order Status)
Table for Orders (Order No, Order Date, Type of widgets, Quantity of Widgets, Order Status)
Table for Backordered Orders (Order No, Order Date)
Table for Widgets (Widget Type, Widget Quantity, Widgets at each station1, station2, station3)
Relationships of the tables
Primary Key and foreign keys in each table
Customer App
Place Order
Query Order Status
Display of Widgets
Supervisor App
Take Order
Monitor Order status
Monitor Overall status
Monitor robot status
Add Inventory
Debit inventory
Process Backordered order
Process order
Robot
Move
Load
Unload
Stop
Defect Fixing
| Testing | Test plan, Test cases dev, test cases execution | Test Plan
Test Cases Dev
Test Cases Exec
Integration Testing
Regression Testing
Defect logging into repository
Defect tracking

## Summary
Estimation Technique | Wideband Delphi
Estimation Unit | Person Hours
Total Estimate | 555.5
Acronyms
A | Analysis
D | Design
Im | Implementation
Int | Integration
T | Testing

## WBS_Estimation
Component | Task ID | Tasks | Scenario | Est | Optimistic |  |  |  |  | Pessimistic |  |  |  |  | MostLikely |  |  |  |  | Estimate | O | P | M | Estimate
[5 empty] | A | D | Im | Int | T | A | D | Im | Int | T | A | D | Im | Int | T |  |  |  |  | A | D | Im | Int | T | Total
Customer Application | WTC-01 | Fetch the widgets from the Inventory | UC 01 | 15 | 3 | 2 | 5 | 2 | 2 | 6 | 3 | 7 | 3 | 2 | 4 | 2 | 6 | 2 | 2 | 16.5 | 14 | 21 | 16 | 4.1667 | 2.1667 | 6 | 2.1667 | 2 | 16.5
| WTC-02 | Display the Type of the Widgets |  | 15 | 3 | 3 | 5 | 3 | 1 | 6 | 5 | 7 | 5 | 2 | 4 | 4 | 7 | 4 | 2 | 20.6667 | 15 | 25 | 21 | 4.1667 | 4 | 6.6667 | 4 | 1.8333 | 20.6667
| WTC-03 | Send the order to the Warehouse | UC 01 | 15 | 1 | 2 | 5 | 3 | 1 | 3 | 3 | 7 | 5 | 2 | 1 | 2 | 6 | 4 | 2 | 15.3333 | 12 | 20 | 15 | 1.3333 | 2.1667 | 6 | 4 | 1.8333 | 15.3333
| WTC-04 | Display the status of order | UC 01 | 20 | 2 | 4 | 5 | 3 | 2 | 3 | 7 | 7 | 5 | 2 | 2 | 6 | 7 | 4 | 2 | 20.6667 | 16 | 24 | 21 | 2.1667 | 5.8333 | 6.6667 | 4 | 2 | 20.6667
| WTC-05 | Error handling | UC 01 | 20 | 2 | 4 | 5 | 3 | 1 | 3 | 7 | 7 | 5 | 2 | 2 | 6 | 7 | 4 | 2 | 20.5 | 15 | 24 | 21 | 2.1667 | 5.8333 | 6.6667 | 4 | 1.8333 | 20.5
Supervisor Application | WTS-01 | display the Order status | UC 02 | 15 | 2 | 2 | 5 | 6 | 1 | 3 | 3 | 7 | 8 | 2 | 2 | 3 | 8 | 8 | 2 | 21.8333 | 16 | 23 | 23 | 2.1667 | 2.8333 | 7.3333 | 7.6667 | 1.8333 | 21.8333
| WTS-02 | provide an interface to handle backordered order | UC 02 | 20 | 2 | 2 | 6 | 4 | 2 | 3 | 4 | 7 | 6 | 2 | 2 | 4 | 7 | 6 | 2 | 20.3333 | 16 | 22 | 21 | 2.1667 | 3.6667 | 6.8333 | 5.6667 | 2 | 20.3333
| WTS-03 | provide an interface to create new inventory entry for Inventory Stations | UC 03 | 20 | 2 | 2 | 6 | 4 | 2 | 3 | 3 | 7 | 6 | 2 | 2 | 3 | 7 | 6 | 2 | 19.5 | 16 | 21 | 20 | 2.1667 | 2.8333 | 6.8333 | 5.6667 | 2 | 19.5
| WTS-04 | The Supervisor Application shall provide an interface to add the number of widgets in Inventory Stations. | UC 03 | 20 | 2 | 2 | 5 | 6 | 2 | 3 | 3 | 7 | 8 | 2 | 2 | 3 | 6 | 8 | 2 | 20.6667 | 17 | 23 | 21 | 2.1667 | 2.8333 | 6 | 7.6667 | 2 | 20.6667
| WTS-05 | display the robot information | UC 04 | 15 | 2 | 2 | 5 | 5 | 2 | 3 | 4 | 7 | 7 | 2 | 2 | 3 | 6 | 6 | 2 | 19.1667 | 16 | 23 | 19 | 2.1667 | 3 | 6 | 6 | 2 | 19.1667
| WTS-06 | When an error happens, the supervisor can order recovery action. | UC 05 | 15 | 2 | 2 | 6 | 6 | 1 | 3 | 4 | 9 | 13 | 2 | 2 | 3 | 8 | 12 | 2 | 26 | 17 | 31 | 27 | 2.1667 | 3 | 7.8333 | 11.1667 | 1.8333 | 26
| WTS-07 | display the Inventory information | UC 07 | 15 | 2 | 2 | 5 | 5 | 2 | 3 | 4 | 7 | 8 | 2 | 3 | 3 | 6 | 6 | 2 | 20 | 16 | 24 | 20 | 2.8333 | 3 | 6 | 6.1667 | 2 | 20
Warehouse System | WTW-01 | shall take the orders from the customers | UC 01 | 20 | 2 | 2 | 6 | 5 | 1 | 4 | 4 | 7 | 8 | 2 | 3 | 3 | 7 | 6 | 2 | 20.8333 | 16 | 25 | 21 | 3 | 3 | 6.8333 | 6.1667 | 1.8333 | 20.8333
| WTW-02 | maintain customer orders with Queue (FIFO) | UC 05 | 20 | 2 | 2 | 6 | 5 | 2 | 4 | 4 | 8 | 8 | 2 | 3 | 3 | 7 | 6 | 2 | 21.1667 | 17 | 26 | 21 | 3 | 3 | 7 | 6.1667 | 2 | 21.1667
| WTW-03 | Maintain backordered orders with another Queue. | UC 05 | 20 | 2 | 2 | 6 | 5 | 2 | 4 | 4 | 8 | 8 | 2 | 4 | 3 | 7 | 6 | 2 | 21.8333 | 17 | 26 | 22 | 3.6667 | 3 | 7 | 6.1667 | 2 | 21.8333
| WTW-04 | move the robot to the next station till all the items of the order are loaded | UC 05 | 20 | 2 | 2 | 4 | 6 | 4 | 4 | 4 | 6 | 9 | 10 | 3 | 3 | 5 | 8 | 8 | 26.5 | 18 | 33 | 27 | 3 | 3 | 5 | 7.8333 | 7.6667 | 26.5
| WTW-04 | the warehouse system debits corresponding widgets from entries in Inventory | UC 05 | 20 | 2 | 2 | 6 | 5 | 4 | 4 | 4 | 10 | 7 | 8 | 4 | 3 | 8 | 6 | 6 | 26.6667 | 19 | 33 | 27 | 3.6667 | 3 | 8 | 6 | 6 | 26.6667
| WTW-05 | move the robot to the shipping station after the order is filled | UC 05 | 20 | 2 | 2 | 5 | 6 | 4 | 4 | 4 | 10 | 8 | 8 | 3 | 3 | 8 | 8 | 6 | 27.5 | 19 | 34 | 28 | 3 | 3 | 7.8333 | 7.6667 | 6 | 27.5
| WTW-06 | History of the stations visited by robot |  | 20 | 2 | 2 | 6 | 3 | 3 | 5 | 4 | 9 | 5 | 4 | 4 | 3 | 8 | 4 | 4 | 22.5 | 16 | 27 | 23 | 3.8333 | 3 | 7.8333 | 4 | 3.8333 | 22.5
| WTW-07 | Updation of order status | UC 05 | 20 | 2 | 2 | 6 | 3 | 3 | 5 | 4 | 8 | 5 | 4 | 4 | 3 | 7 | 4 | 4 | 21.6667 | 16 | 26 | 22 | 3.8333 | 3 | 7 | 4 | 3.8333 | 21.6667
| WTW-08 | Updation of overall status |  | 20 | 2 | 2 | 5 | 3 | 3 | 5 | 4 | 8 | 5 | 4 | 4 | 4 | 6 | 4 | 4 | 21.5 | 15 | 26 | 22 | 3.8333 | 3.6667 | 6.1667 | 4 | 3.8333 | 21.5
Robot | WTR-01 | Move forward |  | 6 | 1 | 2 | 1 | 2 | 3 | 2 | 3 | 3 | 4 | 4 | 1 | 2 | 2 | 3 | 3 | 11.5 | 9 | 16 | 11 | 1.1667 | 2.1667 | 2 | 3 | 3.1667 | 11.5
| WTR-02 | Move backward |  | 6 | 1 | 2 | 1 | 2 | 3 | 2 | 3 | 3 | 4 | 4 | 1 | 2 | 2 | 3 | 3 | 11.5 | 9 | 16 | 11 | 1.1667 | 2.1667 | 2 | 3 | 3.1667 | 11.5
| WTR-03 | Turn left |  | 6 | 1 | 2 | 1 | 2 | 3 | 2 | 3 | 3 | 4 | 4 | 1 | 2 | 2 | 3 | 3 | 11.5 | 9 | 16 | 11 | 1.1667 | 2.1667 | 2 | 3 | 3.1667 | 11.5
| WTR-04 | Turn right |  | 6 | 1 | 2 | 1 | 2 | 3 | 2 | 3 | 3 | 4 | 4 | 1 | 2 | 2 | 3 | 3 | 11.5 | 9 | 16 | 11 | 1.1667 | 2.1667 | 2 | 3 | 3.1667 | 11.5
| WTR-05 | Stop |  | 6 | 1 | 2 | 1 | 2 | 3 | 2 | 3 | 3 | 4 | 4 | 1 | 2 | 2 | 3 | 3 | 11.5 | 9 | 16 | 11 | 1.1667 | 2.1667 | 2 | 3 | 3.1667 | 11.5
DB | WTD-01 | Table for Customers |  | 4 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | 5 | 3 | 1 | 2 | 3 | 4 | 2 | 1 | 11.6667 | 7 | 15 | 12 | 2 | 2.8333 | 3.8333 | 2 | 1 | 11.6667
| WTD-02 | Table for Orders |  | 4 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | 5 | 3 | 1 | 2 | 3 | 4 | 2 | 1 | 11.6667 | 7 | 15 | 12 | 2 | 2.8333 | 3.8333 | 2 | 1 | 11.6667
| WTD-03 | Table for OrderDetails |  | 4 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | 5 | 3 | 1 | 2 | 3 | 4 | 2 | 1 | 11.6667 | 7 | 15 | 12 | 2 | 2.8333 | 3.8333 | 2 | 1 | 11.6667
| WTD-04 | Table for Widgets |  | 4 | 1 | 2 | 2 | 1 | 1 | 3 | 3 | 5 | 3 | 1 | 2 | 3 | 4 | 2 | 1 | 11.6667 | 7 | 15 | 12 | 2 | 2.8333 | 3.8333 | 2 | 1 | 11.6667
|  |  |  | 431 | [24 empty] | 555.5